## Chart
Task Name/ Description | Dependent Tasks | Assigned To | Total Workers | Priority | Start Date | Planned End Date | Actual End Date | Budget
Research for project proposal | Create project proposal | Sarah | 2 | Low | 2022-02-02 | 2022-02-04 | 2022-02-05 | 2150
Create project proposal | Data Collection | Lisa | 3 | Medium | 2022-02-05 | 2022-02-10 | 2022-02-08 | 3120
Hold stakeholder meeting | Data Preparation | Dan | 5 | High | 2022-02-11 | 2022-02-16 | 2022-02-11 | 1730
Get C-suite approval | Dashboard Design | Melissa | 2 | Critical | 2022-02-15 | 2022-02-22 | 2022-02-14 | 4120
Requirement Gathering | Data Entry | Raj | 4 | High | 2022-02-18 | 2022-02-28 | 2022-02-17 | 2200
Maintenance and Support | Documentation | Daniel | 2 | Low | 2022-02-15 | 2022-03-06 | 2022-02-20 | 1890
Evaluation and Improvement | Testing | Rick | 6 | Medium | 2022-02-22 | 2022-03-12 | 2022-02-23 | 3130

## Dashboard
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Sheet5
Dependent Tasks | (All)
Row Labels | Count of Task Name/ Description
Critical | 1
High | 2
Low | 2
Medium | 2
Grand Total | 7

## Sheet8
Row Labels | Count of Dependent Tasks
2 | 3
3 | 1
4 | 1
5 | 1
6 | 1
Grand Total | 7

## sheet 4
Sum of Total Workers | Column Labels
Row Labels | Create project proposal | Evaluation and Improvement | Get C-suite approval | Hold stakeholder meeting | Maintenance and Support | Requirement Gathering | Research for project proposal | Grand Total
1730 |  |  |  | 5 |  |  |  | 5
1890 |  |  |  |  | 2 |  |  | 2
2150 | [6 empty] | 2 | 2
2200 | [5 empty] | 4 |  | 4
3120 | 3 | [6 empty] | 3
3130 |  | 6 | [5 empty] | 6
4120 |  |  | 2 |  |  |  |  | 2
Grand Total | 3 | 6 | 2 | 5 | 2 | 4 | 2 | 24
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.